## Warnings
DGS FORM CO-12
(Form Number DGS-30-104, Revised 01/16)
SCHEDULE OF VALUES and CERTIFICATE FOR PAYMENT
Before using this Excel form, please read the following:
If you use Excel 2007 or 2010, you must "enable macros" or save this as a "Macro-Enabled Worksheet".
Users may …
|  |  |  | Users may add, edit, or delete data in the those cells which are highlighted in yellow. (e.g., | )
Users may insert rows by using the Insert New Row button only !
Users may format cells (e.g., bold, underline, italic, font size, etc.)
Users may format rows (e.g., adjust the row height, etc.)
Users should not …
Users should not modify these worksheets in any manner, other than as noted above !
Users should not "unprotect" these worksheets !
Users should not delete rows in these worksheets !
Users should not enter data directly into any cells that are not highlighted in yellow. Many of the other cells contain formulas which may be accidentally overwritten if spreadsheet is unprotected and data is entered directly into the white cells.
WARNING: |  |  |  | Doing any of the above "should not" actions can compromise the integrity of the CO-12 worksheet by overwriting or deleting data and/or formulas. It is not the responsibility of the DGS staff to help correct worksheets which have been corrupted by users not heeding the above warnings.
It is highly recommended users make backup copies before starting each new pay request !

## Instructions
DGS FORM CO-12
(Form Number DGS-30-104, Revised 01/16)
SCHEDULE OF VALUES and CERTIFICATE FOR PAYMENT
MAIN MENU and GENERAL INSTRUCTIONS
Before proceeding, please click here to read important warnings.
Complete each step below in the order listed. |  | If you need assistance, click here.
1. | Make a backup copy of this Excel file
before proceeding to the next step.
For questions regarding Retainage, refer to the notes included within Step 3.
2.
3. |  | New users, please review the instructions
below before completing Parts B & C.
4.
5.
6.
To view the complete "Building Element" classification structure used in PART B, click here.
7.
8. | Save each monthly submittal with a unique file name.
( for example: Project 999-99999 Pay Request 1, Project 999-99999 Pay Request 2, .... )
9. | Sign and submit the CO-12.
NEXT MONTH - Repeat Steps 1 through 9.

## Assistance
(Form Number DGS-30-104, Revised 01/16)
If you need assistance:
For projects constructed under the provisions of the Higher Education Restructuring Act, please direct ALL questions to that institution, otherwise:
For content or procedural questions, such as contingency reductions, contact the Agency Project
Manager or their Architectural/Engineering Consultant, as appropriate.
For problems with the Excel spreadsheet, proper, please enter the information below and e-mail the complete Excel file you are working on as an attachment to the following e-mail address:
capout@dgs.virginia.gov
( Please recall that it is not the responsibility of the DGS staff to help users correct worksheets which
have been corrupted by user's failure to heed the warnings provided earlier. )
Your Name:
Phone Number:
E-mail address:
Agency Project Mgr:
Phone Number:
E-mail address:
Question or Description of Problem:

## General Project Info
STEP 2 - Enter Project and Contract Information
A ) | Enter the following:
Project Number:
Project Title:
Institution/Agency Name:
Location of Work:
A/E Firm Name:
Contractor Name:
Contractor FEIN:
( FEIN = Fed. Employer Identification Number )
Date Contract Executed
Month:
Day:
Year:
|  | NOTE: | Once the above project and contract information have been entered, unless there are any changes,
STEP 2 can be bypassed on future monthly updates.
B )

## Initialize
STEP 3 - Prepare the CO-12 for New Pay Period
WARNING: Run the Initialize Macro only once before beginning each
new monthly pay request. See the explanation below.
[6 empty] | Today is: | 2019-08-13
A ) | [5 empty] | NOTE: This form was last initialized on: | 2015-03-19
B ) | Update the following data:
| Pay Request Number: |  | 1
For Pay Period Beginning:
For Pay Period Ending:
Pay Request Submittal Date:
Contractor Representative:
C ) |  | * | Retainage is initially set at the default value of 5%. With the Owner's PRE-APPROVAL, the retainage percentage may be adjusted. DO NOT ADJUST the retainage value UNTIL AFTER the INITIALIZE macro is run.
For the final pay request, adjusting the retainage value to 0%, AFTER the INITIALIZE macro is run, will release remaining retainage, if approved by the Owner.
Initializing Explained ---- what is does and how it works:
Initializing is designed to save the user considerable time and effort.
Initializing the CO-12 Form runs a macro (an automated procedure) which prepares the CO-12
for data entry for each new pay application. The macro copies all of the data from the
"Current Value to Date" column to the "Previous Value to Date" column as shown in the
example below.
This step must be done to compute the correct values for the current pay request.
| Example: |  |  |  | VALUE OF WORK COMPLETED
|  |  |  | PREVIOUS | VALUE | CURRENT
|  |  | TOTAL | VALUE | THIS | VALUE | PERCENT
|  |  | VALUE | TO DATE | REPORT | TO DATE | COMPLETE
| Before initializing: |  | 100 | 20 | 10 | 30 | 30%
Cells with a yellow background
allow data input by the user.
| After initializing: |  | 100 | 30 | 0 | 30 | 30%
Cells with a white background are
calculated cells. These cells are "locked"
| After updating %: |  | 100 | 30 | 20 | 50 | 50% | to prevent the user from accidentially
overwriting the embedded formulas.
The "Initialize" macro copies all "Current Value to Date" entries to the "Previous Value to Date" column.
After the initializing macro is run, you can now update the "Percent Complete" column to reflect new progress.
After updating the "Percent Complete" column, the new "Current Value to Date" amount is calculated by
a formula which multiplies the "Percent Complete" by the "Total Value".
Another formula calculates the "Value This Report" amount by subtracting the "Previous Value
to Date" amount from the "Current Value to Date" amount.
a
a
b
c
d
b
c
d

## PART A
STEP 6 - Review PART A |  |  |  | NOTE: All information on the PART A page is updated from entries made in the other steps.
|  |  | Return to General Instructions | If any information on the PART A summary appears incorrect, return to the appropriate step
and make changes as required.
DGS-30-104 ( FORM CO-12 ) |  | SCHEDULE OF VALUES |  |  |  | PAYMENT REQUEST NO. |  | 1
(Rev. 01/16) |  | and
PART A | [6 empty] | PERIOD BEGINNING DATE: | 0
SUMMARY AND CERTIFICATION |  | CERTIFICATE FOR PAYMENT |  |  |  |  | PERIOD ENDING DATE: | 0
| PROJECT CODE: | 0
| AGENCY NAME: | 0
| PROJECT TITLE: | 0
VALUE OF WORK COMPLETED
[5 empty] | PREVIOUS | VALUE | CURRENT
|  |  |  | TOTAL | VALUE | THIS | VALUE | PERCENT
|  |  |  | VALUE | TO DATE | REPORT | TO DATE | COMPLETE
|  |  |  | A | B | C | D = B + C | E = D / A
Original Contract Line Items (from CO-12, PART B) |  |  |  | 0 | 0 | 0 | 0 | 0%
Approved Change Orders (from CO-12, PART C) |  |  |  | 0 | 0 | 0 | 0 | 0%
ADJUSTED CONTRACT TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0%
Retainage | Retainage Percentage: | #DIV/0! |  |  | 0 | 0 | 0
NET REQUISTION AMOUNT |  |  |  |  | 0 | 0 | 0
Amount Requested
CONTRACTOR CERTIFICATION
The undersigned Contractor requests payment of that portion of the contract price shown on the last line
of the foregoing Schedule of Values, and represents and warrants to the Owner that: (1) the data shown on the
Schedule of Values is accurate and correct; (2) the Work covered by this Certificate has been completed in
accordance with the Contract Documents; (3) all previous progress payments received from Owner on account of Work done
under this Contract have been applied to discharge in full (except for allowable retainage) all obligations of Contractor
incurred in connection with Work covered by prior Certificates for Payment ( not applicable for Pay Request 1 ) ;
(4) title to all materials and equipment for which payment is requested in this Certificate, whether or not incorporated
in said Work, will pass to Owner at time of payment free and clear of all liens, claims, security interests and
encumbrances (except such materials and equipment which are covered by a Bond previously accepted by Owner).
FEIN #: | *** enter FEIN in Step 2 *** |  |  | Contractor: | *** enter Contractor name in Step 2 ***
Date: | 0 |  |  | By:
signature
|  |  |  | Typed Name: | *** enter Contractor Representative's Name in Step 3 ***
ARCHITECT/ENGINEER CERTIFICATION
This is to certify that, in accordance with the terms of a contract for Project Number executed
the day of , by and between, ,
the contractor, and the Commonwealth of Virginia, ,
the Owner, for work at , there is due to the Contractor the amount of
#NAME?
Architect/Engineer:
By:
| signature |  |  |  | printed name |  | date
AGENCY ACTION
Amount approved for payment this certificate is:
Dollars ( )
By:
| signature |  |  |  | title |  | date
By:
| signature |  |  |  | title |  | date

## PART B
STEP 4 - Complete PART B
DGS-30-104 ( FORM CO-12 ) |  |  | SCHEDULE OF VALUES AND CERTIFICATE FOR PAYMENT | [6 empty] | PAYMENT REQUEST NO. | [5 empty] | 1
(Rev. 01/16) |  |  | PROJECT CODE: | 0
PART B |  |  | AGENCY NAME: | 0 | [9 empty] | PERIOD BEGINNING DATE: |  | 0
ORIGINAL CONTRACT LINE ITEMS |  |  | PROJECT TITLE: | 0 | [9 empty] | PERIOD ENDING DATE: |  | 0
VALUE OF WORK COMPLETED
ITEM NO. | BUILDING ELEMENT | ADDITIONAL DESCRIPTION | TOTAL VALUE | PREVIOUS VALUE TO DATE | VALUE THIS REPORT | CURRENT VALUE TO DATE | PERCENT COMPLETE | LINE ITEM RETAINAGE (PERCENT) | LINE ITEM RETAINAGE AMOUNT | VENDOR NAME | Micro | Small | Woman | Minority | Dis Vet | DSBSD CERTIFICATE NUMBER
|  |  | 0 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N |  | 14
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  | DO NOT EDIT OR DELETE. See 2nd note in red above. |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
TOTAL ORIGINAL CONTRACT |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0
Before pressing the "Insert New Row" button, first click on a cell highlighted in yellow. When you then press the "Insert New Row" button, a new row will be added immediately above the selected cell. IMPORTANT: DO NOT EDIT OR DELETE THE LAST YELLOW ROW. The last row, however, may be selected before pressing the "Insert New Row" button to enable rows to be added above it.

## PART C
STEP 5 - Complete PART C
DGS-30-104 ( FORM CO-12 ) |  | SCHEDULE OF VALUES AND CERTIFICATE FOR PAYMENT | [6 empty] | PAYMENT REQUEST NO. | [5 empty] | 1
(Rev. 01/16) |  | PROJECT CODE: | 0
PART C |  | AGENCY NAME: | 0 | [8 empty] | PERIOD BEGINNING DATE: |  |  | 0
CONSTRUCTION CHANGE ORDERS |  | PROJECT TITLE: | 0 | [8 empty] | PERIOD ENDING DATE: |  |  | 0
VALUE OF WORK COMPLETED
CHNG. ORD. NO. | ITEM DESCRIPTION | TOTAL VALUE | PREVIOUS VALUE TO DATE | VALUE THIS REPORT | CURRENT VALUE TO DATE | PERCENT COMPLETE | LINE ITEM RETAINAGE (PERCENT) | LINE ITEM RETAINAGE AMOUNT | VENDOR NAME | Micro | Small | Woman | Minority | Dis Vet | DSBSD CERTIFICATE NUMBER
|  | 0 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N |  | 12
|  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
|  |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
| DO NOT EDIT OR DELETE. See 2nd note in red above. |  | 0 | 0 | 0 |  | 5% | 0 |  | N | N | N | N | N
TOTAL APPROVED CHANGE ORDERS |  | 0 | 0 | 0 | 0 | 0% | 0% | 0
Before pressing the "Insert New Row" button, first click on a cell highlighted in yellow. When you then press the "Insert New Row" button, a new row will be added immediately above the selected cell. IMPORTANT: DO NOT EDIT OR DELETE THE LAST YELLOW ROW. The last row, however, may be selected before pressing the "Insert New Row" button to enable rows to be added above it.

## Print
STEP 7 - Print the CO-12

## PART B Instructions
PART B Instructions
The ORIGINAL CONTRACT line items ( and progress for same ) are entered in PART B of the CO-12 form.
Below is an example PART B with detailed instructions shown in red.
VALUE OF WORK COMPLETED
ITEM NO. | BUILDING ELEMENT | ADDITIONAL DESCRIPTION | TOTAL VALUE | PREVIOUS VALUE TO DATE | VALUE THIS REPORT | CURRENT VALUE TO DATE | PERCENT COMPLETE | LINE ITEM RETAINAGE (PERCENT) | LINE ITEM RETAINAGE AMOUNT | VENDOR NAME | Micro | Small | Woman | Minority | Dis Vet | DSBSD CERTIFICATE NUMBER
100 L | B1010 Floor Construction | Structural Steel Material | 5675 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
Enter a unique number for each line item. ( Examples: 1, 2, 3….. 1A, 1B, 1C…… 100, 200, 300….. 100.1, 100.2, 100.3. ) No specific format is mandated for Item Number field.
500 | G2020 Parking Lots | Lot A | 30000 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
Select a Building Element from the ASTM Uniformat list. Building Elements may be entered multiple times.
Enter additional description of the work item ( e.g., floor, wing, etc.), as needed, to provide sufficient detail for progress to be assessed.
( For Example: 1st Floor, 2nd Floor, …., East Wing, West Wing, …., Chiller A, Chiller B, …. etc.)
501 | G2020 Parking Lots | Lot B | 50000 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
If payment will be sought for stored materials, labor and materials must be shown on separate lines.
Provide other supporting documentation as required by the General Conditions.
100 L | B1010 Floor Construction | Structural Steel Material | 5675 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
100 M | B1010 Floor Construction | Structural Steel Installation | 0 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
Enter the original contract value for each line item.
100 L | B1010 Floor Construction | Structural Steel Material | 5675 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
Do not enter data in these columns. (These values are computed by worksheet formulas. )
500 | G2020 Parking Lots | Lot A | 30000 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
Enter the total progress (percent complete) for each line item. | [8 empty] | Enter the retainage percentage for each line item.
501 | G2020 Parking Lots | Lot B | 50000 | 0 | 22500 | 22500 | 45% | 5% | 1125 |  | N | N | N | N | N
If subcontractor is a Small (S), Woman (W), or Minority (M) - owned business, enter vendor name, and Yes (Y) or No (N) for S, W, M status.
502 | G2020 Parking Lots | Lot C | 30000 | 0 | 7500 | 7500 | 25% | 5% | 375 | Smith's Paving Services | N | N | N | N | N | 99999-999
If subcontractor is a Small (S), Woman (W), or Minority (M) - owned business, enter their Department of Minority Business Enterprise (DMBE) certificate number.

## PART C Instructions
PART C Instructions
The CONSTRUCTION CHANGE ORDERS ( and progress for same ) are entered in PART C of the CO-12 form.
Below is an example PART C with detailed instructions shown in red.
VALUE OF WORK COMPLETED
ITEM NO. | BUILDING ELEMENT | TOTAL VALUE | PREVIOUS VALUE TO DATE | VALUE THIS REPORT | CURRENT VALUE TO DATE | PERCENT COMPLETE | LINE ITEM RETAINAGE (PERCENT) | LINE ITEM RETAINAGE AMOUNT | VENDOR NAME | Micro | Small | Woman | Minority | Dis Vet | DSBSD CERTIFICATE NUMBER
1 | ADDITIONAL LANDSCAPING | 10000 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
Enter the Change Order Number. ( Examples: 1, 2, 3…..). Additional identifying numbers and/or letters may be added as shown in examples below as needed.
1a | ADDITIONAL LANDSCAPING - Additional trees and shrubs | 6000 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
1b | ADDITIONAL LANDSCAPING - Extend irrigation system | 4000 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
If necessary to provide more detail for a specific Change Order, use multiple lines for each component as needed.
3 | EPDM Roofing | 0 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
Enter a Change Order description. ( Line items must be broken out in a sufficient level of detail to allow Owner and A/E to assess progress. )
If payment will be sought for stored materials, labor and materials must be entered on separate lines.
4 L | Structural Steel - Installation | 0 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
4 M | Structural Steel - Materials | 0 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
Enter the scheduled value for each Change Order or component thereof.
5 L | Structural Steel - Installation | 5675 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
Do not enter data in these columns. (These values are computed by worksheet formulas. )
6.1 | Pave Parking Lot A | 30000 | 0 | 0 | 0 | 0% | 5% | 0 |  | N | N | N | N | N
Enter the total progress (percent complete) for each line item.
6.2 | Pave Parking Lot B | 50000 | 0 | 37500 | 37500 | 75% | 5% | 1875 |  | N | N | N | N | N
If subcontractor is a Small (S), Woman (W), or Minority (M) - owned business, enter vendor name, and Yes (Y) or No (N) for S, W, M status.
6.3 | Pave Parking Lot C | 30000 | 10000 | 20000 | 30000 | 100% | 5% | 1500 | Smith's Paving Services | N | N | N | N | N | 99999-999
If subcontractor is a Small (S), Woman (W), or Minority (M) - owned business, enter their Department of Minority Business Certificate (DMBE) certificate number.

## Days
first
second
third
fourth
fifth
sixth
seventh
eighth
ninth
tenth
eleventh
twelfth
thirteenth
fourteenth
fifthteenth
sixteenth
seventeenth
eighteenth
nineteenth
twentieth
twenty-first
twenty-second
twenty-third
twenty-fourth
twenty-fifth
twenty-sixth
twenty-seventh
twenty-eighth
twenty-ninth
thirtieth
thirty-first

## Code
Use the Level III classification to describe Building Elements in the Schedule of Values.
Extracted, with permission, from ASTM E1557-09 Standard Classification for Building Elements and Related Sitework-UNIFORMAT II, copyright ASTM International, 100 Barr Harbor Drive, West Conshohocken, PA 19428. A copy of the complete standard may be obtained from ASTM International, www.astm.org.
( Click here to visit astm.org )
| Level I | Level II | Level III
Code
| A Substructure | A10 Foundations | A1010 Standard Foundations
A1020 Special Foundations
A1030 Slab on Grade
|  | A20 Basement Construction | A2010 Basement Excavation
A2020 Basement Walls
| B Shell | B10 Superstructure | B1010 Floor Construction
B1020 Roof Construction
|  | B20 Exterior Enclosure | B2010 Exterior Walls
B2020 Exterior Windows
B2030 Exterior Doors
|  | B30 Roofing | B3010 Roof Coverings
B3020 Roof Openings
| C Interiors | C10 Interior Construction | C1010 Partitions
C1020 Interior Doors
C1030 Fittings
|  | C20 Stairs | C2010 Stair Construction
C2020 Stair Finishes
|  | C30 Interior Finishes | C3010 Wall Finishes
C3020 Floor Finishes
C3030 Ceiling Finishes
| D Services | D10 Conveying | D1010 Elevators & Lifts
D1020 Escalators & Moving Walks
D1090 Other Conveying Systems
|  | D20 Plumbing | D2010 Plumbing Fixtures
D2020 Domestic Water Distribution
D2030 Sanitary Waste
D2040 Rain Water Drainage
D2090 Other Plumbing Systems
|  | D30 HVAC | D3010 Energy Supply
D3020 Heat Generating Systems
D3030 Cooling Generating Systems
D3040 Distribution Systems
D3050 Terminal & Package Units
D3060 Controls & Instrumentation
D3070 System Testing & Balancing
D3090 Other HVAC Systems & Equipment
|  | D40 Fire Protection | D4010 Sprinklers
D4020 Standpipes
D4030 Fire Protection Specialties
D4090 Other Fire Protection Systems
|  | D50 Electrical | D5010 Electrical Service & Distribution
D5020 Lighting and Branch Wiring
D5030 Communications & Security
D5090 Other Electrical Systems
| E Equipment & Furnishings | E10 Equipment | E1010 Commercial Equipment
E1020 Institutional Equipment
E1030 Vehicular Equipment
E1090 Other Equipment
|  | E20 Furnishings | E2010 Fixed Furnishings
E2020 Movable Furnishings
| F Special Construction & Demolition | F10 Special Construction | F1010 Special Structures
F1020 Integrated Construction
F1030 Special Construction Systems
F1040 Special Facilities
F1050 Special Controls and Instrumentation
|  | F20 Selective Building Demolition | F2010 Building Elements Demolition
F2020 Hazardous Components Abatement
| G Sitework & Utilities | G10 Site Preparation | G1010 Site Clearing
G1020 Site Demolition and Relocations
G1030 Site Earthwork
G1040 Hazardous Waste Removal
|  | G20 Site Improvements | G2010 Roadways
G2020 Parking Lots
G2030 Pedestrian Paving
G2040 Site Development
G2050 Landscaping
|  | G30 Site Mechanical Utilities | G3010 Water Supply
G3020 Sanitary Sewer
G3030 Storm Sewer
G3040 Heating Distribution
G3050 Cooling Distribution
G3060 Fuel Distribution
G3090 Other Site Mechanical Utilities
|  | G40 Site Electrical Utilities | G4010 Electrical Distribution
G4020 Site Lighting
G4030 Site Communications & Security
G4090 Other Site Electrical Utilities
|  | G90 Other Site Construction | G9010 Services and Pedestrian Tunnels
G9090 Other Site Systems & Equipment
* | Z Gen'l. Cond. / OH&P | Z Gen'l. Cond. / OH&P | Z0000 General Conditions / Gen'l Requirements, OH & P
* - | The last entry above is not part of the referenced ASTM Uniformat II classification standard.
Click here to view PART B costs summarized by Building Element.