## Comment & Response Log
Comment & Response Log
Project Name: | VIMS - Facilities Management Building
Project Number: | 268-18088
Agency: | VIMS
Design Phase | A/E Submittal Dated | CRT Received | CRT Comments Dated
Conceptual Design
Schematic Design
Working Drawings
WD - Revision #1
WD - Revision #2
WD - Revision #2
Permit Set

## Building Permit Checklist
Building Permit Checklist
Project Name: | VIMS - Facilities Management Building
Project Number: | 268-18088
Agency: | VIMS
Permit Item | A/E Submittal Dated | Received | Returned | Accepted

## CO Checklist
Certificate of Occupancy Requirements
Project Name: | VIMS - Facilities Management Building
Project Number: | 268-18088
Agency: | VIMS
Certificate of Occupancy | Dated (Date Revised) | Received in CRT Office | Returned to FPDC PM by CRT | Accepted / Rejected by CRT
Submittals Completed
Delegated Designs
D&F's
Shop Drawings
Bulletins
Documentation (Including all Attachments)
HECO-13.3 - Application for Certificate of Use and Occupancy Rev. 3-4-15
or
HECO-13.3c - Acknowledgement of Substantial and Final Completion Rev. 3-4-15
Test Results & Certifications
Backflow Prevention Certification Test Results
Commissioning Procedures
EH&S Equipment Certifications
Elevator Certificate(s)
Elevator Communication System(s)
Emergency Communication System
Emergency Lighting Test
Fall Protection
Fire Alarm Test(s):
Contractor Pre-Test
CRT Pre-Test
SFMO Acceptance Test(s)
Fire Pump Test
Health Department Certificate
Lightning Protection System Master Label
Stand Pipe Flow Test
Waterline Bacteriological Test Results
Additional Specification Required Tests
Inspections
Rough-Ins
Above Ceilings
Utility Rooms
Panel Board & Associated Electrical Systems
Service Entrance
Pre-Substantial & Substantial Inspections
Emergency Power Systems
Mechanical Systems, including Fire Dampers
Fire Dampers
Plumbing Systems
Fire Rated Assemblies
Egress Pathways & Components
Code Required Signage
Additional Specification Required Inspection(s)