## Sheet1
|  |  |  | DESIGN & CONSTRUCTION RED ZONE CHECKLIST | [7 empty] | 115 Grigsby Drive
Williamsburg, VA 23187-8795
https://wm.edu/architect
Critical Activity Section | Task | Responsibility | [7 empty] | Completion / Turnover Date (planned) | Completion / Turnover Date (actual) | Notes
|  | C | O&M | PM | BAS | A/E | IT | USER | V
SYSTEM COMPONENT STAR TUP | AHU Startup Checklist / Startup | [10 empty] | Provide 7 days notice to CxA | bar: Responsibility C
| VFD Startup Checklist / Startup | [10 empty] | Provide 7 days notice to CxA | bar: Responsibility C
| Heat exchanger startup checklist / startup | [10 empty] | Provide 7 days notice to CxA | bar: Responsibility C
| Return Fan startup checklist / startup | [10 empty] | Provide 7 days notice to CxA | bar: Responsibility C
| Pumps startup checklist / startup | [10 empty] | Provide 7 days notice to CxA | bar: Responsibility C
| Exhaust fan startup checklist / startup | [10 empty] | Provide 7 days notice to CxA | bar: Responsibility C
| Split system startup checklist / startup | [10 empty] | Provide 7 days notice to CxA | bar: Responsibility C
| Boiler startup | [10 empty] | Provide 7 days notice to CxA | bar: Responsibility C
| Boiler testing | [10 empty] | Provide 7 days notice to CxA | bar: Responsibility C
| Boiler certification (sent to O&M) | [10 empty] | Send to Utilities Supervisor and AD for Utilities | bar: Responsibility C
Outline/schedule of systems requiring O&M PM during warranty period | bar: Responsibility C
TESTING AND BALANCING | 1st Season TAB (air) | [10 empty] | Pre-checklist available | bar: Responsibility C
| 1st Season TAB (water) | [10 empty] | Pre-checklist available | bar: Responsibility C
| 1st Season TAB report to be submitted | [10 empty] | Copy of Report to be sent to AD of Operations & Maintenance | bar: Responsibility C
1st Season TAB verification | bar: Responsibility C
2nd Season TAB (air) | bar: Responsibility C
2nd Season TAB (water) | bar: Responsibility C
| 2nd Season TBA report to be submitted | [10 empty] | Copy of Report to be sent to AD of Operations & Maintenance | bar: Responsibility C
2nd Season TAB verification | bar: Responsibility C
| Fire Alarm shut down of AHU | [10 empty] | requires CxA witness | bar: Responsibility C
DALT (duct leakage) testing / report | bar: Responsibility C
Confirmation of building pressurization (.05" WC per Tehnical Stanards) | bar: Responsibility C
BAS | BAS clipping | bar: Responsibility C
BAS point to point | bar: Responsibility C
Notification BAS point to point completed | bar: Responsibility C
BAS point to point verification (CxA) | bar: Responsibility PM to Responsibility BAS
BAS sequence commissioning checkout | bar: Responsibility C
Meter data connection verification | bar: Responsibility C; Responsibility BAS; Responsibility IT
OTHER MECHANICAL ITEMS | Chemical added to hot water system | [10 empty] | Fill and flush | bar: Responsibility C
Chemical report for HW (sent to O&M) | bar: Responsibility C
| Chemical added to chilled water | [10 empty] | Fill and flush | bar: Responsibility C
Chemical report for CW (sent to O&M) | bar: Responsibility C
Insurance review of fire protection | bar: Responsibility PM
| Fume hoods - ASHRAE 110 test records | [10 empty] | Requires CxA witness | bar: Responsibility C
Fume hood verification by CxA | bar: Responsibility PM
Environmental rooms - spot check access conflicts | bar: Responsibility O&M to Responsibility PM
Environmental room startup | bar: Responsibility C
| Environmental room training | [10 empty] | 3rd party - training of A&S staff | bar: Responsibility C
Backflow testing | bar: Responsibility C
| Fire Suppression - Sprinkler testing | [10 empty] | Fire Maintenance Supervisor to witness | bar: Responsibility C
Super chlorination of potable water systems | bar: Responsibility C
Meter installation (steam) | bar: Responsibility C
Meter commissioning/verification (steam) | bar: Responsibility PM to Responsibility BAS
Meter training (steam) | bar: Responsibility C
Meter installation (water) | bar: Responsibility C
Meter commissioning/verification (water) | bar: Responsibility PM to Responsibility BAS
Meter training (water) | bar: Responsibility C
Outline/schedule of systems requiring O&M PM during warranty period | bar: Responsibility C
ELECTRICAL | Arc flash labels installed | bar: Responsibility C; Responsibility A/E
| Arc flash final report (sent to O&M) | [10 empty] | ensure initial study is updated per submitted equipment | bar: Responsibility A/E
Breaker and relay settings report | bar: Responsibility A/E
Transformer performance verification | bar: Responsibility C
Meter installation (electrical) | bar: Responsibility C
Meter commissioning/verification (electrical) | bar: Responsibility PM to Responsibility BAS; Responsibility IT
Meter training (electrical) | bar: Responsibility C
| Data as-built and test report | [10 empty] | pencil copy; FINAL COPY TO BE INCLUDED WITH CLOSEOUT DOCS | bar: Responsibility C
| Fire Alarm NFPA 72 testing | [10 empty] | notification via outage request | bar: Responsibility C
| NFPA 72 test report (sent to O&M Fire Maint. Supervisor) | [10 empty] | pencil copy; FINAL COPY TO BE INCLUDED WITH CLOSEOUT DOCS | bar: Responsibility C
Generator testing | bar: Responsibility C
Generator performance verification | bar: Responsibility PM to Responsibility BAS
Notify EH&S of emissions date | bar: Responsibility C; Responsibility PM
Outline/schedule of systems requiring O&M PM during warranty period | bar: Responsibility C
TRAINING | Mechanical training: (system) | [10 empty] | required within 7 days of move-in
| Mechanical training: (system) | [10 empty] | required within 7 days of move-in
| Mechanical training: (system) | [10 empty] | required within 7 days of move-in
| Mechanical training: (system) | [10 empty] | required within 7 days of move-in
| Electrical training: (system) | [10 empty] | required within 7 days of move-in
| Electrical training: (system) | [10 empty] | required within 7 days of move-in
| Electrical training: (system) | [10 empty] | required within 7 days of move-in
AV training | bar: Responsibility PM
PRE-MOVE IN | IT data activations | bar: Responsibility PM; Responsibility IT to Responsibility USER
Provide programming requirements for access control | bar: Responsibility USER
Access Control programming & activations | bar: Responsibility O&M to Responsibility PM; Responsibility USER
Keying meeting (verification of outcomes of design phase keying meeting) | bar: Responsibility O&M to Responsibility PM; Responsibility USER
FF&E Operations & Maintenance manuals | bar: Responsibility O&M to Responsibility PM
| Door cores installed | [10 empty] | includes FAMIS request to remove construction cores | bar: Responsibility O&M to Responsibility PM
OTHER | Fall protection certification | bar: Responsibility C
Construction fence removal | bar: Responsibility C
Final landscaping | bar: Responsibility C
PUNCH LIST | Punchlist - above ceiling | bar: Responsibility PM; Responsibility A/E
Punchlist - above ceiling approval | bar: Responsibility PM; Responsibility A/E
Punchlist - architectural | bar: Responsibility C to Responsibility O&M; Responsibility A/E
Punchlist - engineering | bar: Responsibility A/E
Punchlist distributed to contractor | bar: Responsibility A/E
Punchlist distributed to Inspector and O&M | bar: Responsibility PM
DCM FIGURE 14.1 CLOSEOUT REQUIREMENTS | HECO-17 Building Permit
CO-13.3a Application for Certificate(s) of Use and Occupancy
HECO-13.3c, 13.3d Acknowledgement of Substantial/Final Completion
| CO-14 Close-Out Document | [10 empty] | final completion of e-Builder PCL process
CO/HECO 13 Affidavit of Claims | bar: Responsibility C
CO/HECO 13.1 Certificate of Completion by A/E or PM | bar: Responsibility PM; Responsibility A/E
CO/HECO 13.1a Certificate of Substantial Completion | bar: Responsibility A/E
CO/HEOC 13.1b Structural Inspection Report
Elevator Inspection Report
Potable Water Report(s)
Roofing Summary Report / Roof Maintenance Certificate
Roofing Warranty
CO-13.2 Contractor Certificate of Completion | bar: Responsibility C
CO-13.2a Certificate of Partial/Substantial Completion by Contractor | bar: Responsibility C
| HECO-13.3b Checklist for Occupancy | [10 empty] | (Beneficial) (Set-Up) (Partial) | bar: Responsibility PM
State Fire Marshal Letter of Acceptance | bar: Responsibility PM
ADDITIONAL CONTRACT CLOSEOUT REQUIREMENTS | Abatement summary worksheet | bar: Responsibility C
Abatement waste manifests | bar: Responsibility C
Abatement air clearances | bar: Responsibility C
| Data as-built and test reports | [10 empty] | Final copy pdf and DWG | bar: Responsibility C
| O&M manuals, As-Built Drawings, and Warranty forms | [10 empty] | electronic submission for review | bar: Responsibility C
| A/E review of O&Ms, As-Builts, and Warranties | [10 empty] | treat as submittal (14 day TAT) | bar: Responsibility A/E
| Contractor turnover of O&Ms, As-Builts, and Warranties | [10 empty] | digital and hard copies as specified in DCM | bar: Responsibility C
| Distribution of O&Ms, As-Builts, and Warranties | [10 empty] | distribution includes O&M and archiving in eBuilder/Blueprints drive | bar: Responsibility PM
Warranty summary sheet | bar: Responsibility C
Finishes summary sheet | bar: Responsibility C
Door hardware schedule and submittal | bar: Responsibility C; Responsibility PM
Furniture order PO and product detail | bar: Responsibility C; Responsibility PM
| Cleaning Instructions | [10 empty] | distribution to Building Services | bar: Responsibility C; Responsibility PM
Warranty and finishes to facility manager and AD of O&M | bar: Responsibility PM
Fully signed off punch list | bar: Responsibility C
Verify punch list | bar: Responsibility O&M to Responsibility PM; Responsibility A/E
Attic stock turnover | bar: Responsibility C
Final SWaM report | bar: Responsibility C
Certified payroll, all contractors (for prevailing wage projects) | bar: Responsibility C
LEED certification | bar: Responsibility C; Responsibility PM; Responsibility A/E
Process recycled/recovered materials report | bar: Responsibility C
Submission of project record docs as PDF, DWG, and BIM | bar: Responsibility A/E
Submission of georeferenced site and utility drawings | bar: Responsibility A/E
| F-1 Form (FIC Report) | [10 empty] | distribute to Space Management and Fixed Assets | bar: Responsibility PM; Responsibility A/E
| Risk Management Building Information Update Form | [10 empty] | distribute to Risk Management | bar: Responsibility PM
Close-Out Briefing with University Architect and Director of O&M | bar: Responsibility PM
Project Debrief Form Completion (Lessons Learned Spreadsheet) | bar: Responsibility PM
Schedule 10-Month guarantee period walkthrough | bar: Responsibility PM
MOVE-IN | User move-in | bar: Responsibility PM; Responsibility USER
Ribbon cutting or grand opening ceremony | bar: Responsibility USER
Notification of Building Services turnover date | bar: Responsibility PM
Building Services Stock restrooms | bar: Responsibility O&M
Building services provide trash receptacles | bar: Responsibility O&M
PROJECT CLOSEOUT - SUBSTANTIAL COMPLETION +90 DAYS | bar: Responsibility PM
[11 empty] | V | Responsible for Verification
[11 empty] | C | General Contractor (GC) or Construction Manager (CMaR)
[11 empty] | O&M | Facilities Management Operations & Maintenance
[11 empty] | PM | Project Manager (Office of the University Architect)
[11 empty] | BAS | Building Automation Shop
[11 empty] | A/E | Design Professional under Contract (Architect/Engineer)
[11 empty] | USER | User Group
[11 empty] | EH&S | Environmental Health & Safety
[11 empty] | IT | William & Mary IT